## Register
ID | Risk Title | Category | Owner | Date Identified | Description | Cause | Consequence | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Score | Inherent Severity | Existing Controls | Treatment Strategy (Avoid/Reduce/Transfer/Accept) | Treatment Actions | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Score | Residual Severity | Status | Next Review Date | Notes
R-001 | Vendor outage disrupts payroll | Operational | CFO | 2026-01-15 | Critical payroll vendor suffers extended outage | Single-vendor dependency | Payroll delay, staff dissatisfaction, regulatory fines | 3 | 4 | 12 | High | Weekly backups; SLA in contract | Reduce | Onboard secondary payroll provider by Q3 | 2 | 3 | 6 | Medium | Open | 2026-07-01 | Board-visible

## 5x5 Matrix
ISO 31000 5×5 Risk Matrix (Likelihood × Impact)
Likelihood ↓ / Impact → | Impact 1 | Impact 2 | Impact 3 | Impact 4 | Impact 5
Likelihood 5 | 5 · Medium | 10 · High | 15 · Extreme | 20 · Extreme | 25 · Extreme
Likelihood 4 | 4 · Low | 8 · Medium | 12 · High | 16 · Extreme | 20 · Extreme
Likelihood 3 | 3 · Low | 6 · Medium | 9 · Medium | 12 · High | 15 · Extreme
Likelihood 2 | 2 · Low | 4 · Low | 6 · Medium | 8 · Medium | 10 · High
Likelihood 1 | 1 · Low | 2 · Low | 3 · Low | 4 · Low | 5 · Medium

## How to use
Risk Register Template — ISO 31000 aligned
1. Identify — Add one row per risk. Give it a stable ID (R-001, R-002 …).
2. Analyse — Score Inherent Likelihood and Inherent Impact on the 5×5 matrix (before controls).
3. Evaluate — Compare severity against your risk appetite. High/Extreme → treat.
4. Treat — Pick Avoid / Reduce / Transfer / Accept. List concrete actions and owners.
5. Monitor — Score residual likelihood/impact after controls, set a review date, track status.
Severity bands: Score 1–4 Low · 5–9 Medium · 10–14 High · 15–25 Extreme.
When your register outgrows this sheet, move to RiskManager for auditable history, matrix views, and review reminders — https://rskmngr.lovable.app